## Sheet1
| User Story | Sprint Numbers | Story Priority | Story Status | Story Points
1 | As a student, I want to know where study sessions are being held so that I can prepare for exams with my classmates. | 2022-01-04 | H | IP | 4
2 | As an event organizer, I want to know the number of people planning to come to my events so that I can properly prepare concessions and seating. | 4 | M | IP | 4
3 | As a user, I want to know the identities of the people coming to my events so that I can be aware of who is attending. | 6+ | L | W | 3
4 | As a student, I want to know what events my friends are attending so that I can attend with them. | 6+ | L | W | 3
5 | As a member of the University of Maine Police department, I want to know where the big events are so that I can keep people safe. | 2022-01-04 | H | IP | 3
6 | As a user, I want to be able to sort events by most to least popular so that I can go to an event with a gathering size I’m comfortable with. | 4 | M | IP | 2
7 | As a campus faculty member, I want to know what students are doing around campus, so that we can best support their interests. | 4 | M | IP | 3
8 | As a fraternity member, I want to be able to advertise my events so that I can increase participation. | 5 | M | W | 3
9 | As a user, I want my data to be secure so that sensitive information is not exposed. | 5 | M | W | 3
10 | As a user, I want multifactor authentication so that my account is secure. | 5 | M | W | 3
11 | As a business, I want to know when popular events are happening nearby so that I can prepare for increased pedestrian traffic. | 5 | M | W | 4
12 | As a user, I want to be able to log in to my account so I can see events I have committed to. | 2 | H | Done | 3
13 | As a user, I want to be able to use hashtags on my events so that I can easily filter out events I am not interested in. | 6+ | L | W | 2
14 | As a user, I want to be able to choose who can see my event details so that I can prevent unwanted people from attending. | 6+ | L | W | 3
15 | As an event-planner, I want to be able to generate a link for my event so that I can send it to others. | 5 | L | W | 1
16 | As a regular user, I want to be able to set up a recurring event, so that I can avoid the hassle of reposting the same event repeatedly. | 6+ | L | W | 2
17 | As a regular user, I want to be able to see a history of events I have planned and attended so that I can view what I have done previously. | 5 | M | W | 4
18 | As a commuter, I want to be able to see where the closest parking spots are for a certain event so that I can reduce walking time to the event. | 6+ | L | IP | 3
19 | As a user, I want to create a profile so that I can identify myself when I sign up for events. | 2 | H | Done | 4
20 | As a user, I want to customize my profile so that others can learn more about me prior to events. | 3 | H | IP | 3
21 | As a student, I want to create an event for meeting at the union so that I can get lunch with friends. | 2022-01-04 | H | IP | 3