## Sprint Backlog 6
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
3 | As a user, I want to know the identities of the people coming to my events so that I can be aware of who is attending. | 1. Learn how to display a list of an event's committed attendees. 2. Implement a way to view the attendees in the event details contexts. | 6 | Environment creation | F, KA | 3
4 | As a student, I want to know what events my friends are attending so that I can attend with them. | 1. Learn how to create an activity feed that displays the events the user's friends have committed to. 2. Learn how to display a list of events a user has committed to on the user's page. 3. Implement the activity feed and listform event view on user pages. | 6 | Environment creation | F, KA | 3
10 | As a user, I want multifactor authentication so that my account is secure. | 1. Decide which other authentication methods to use for the multifactor authentication. 2. Learn how to integrate multifactor authentication to the existing login process. 3. Implement multifactor authentication. | 6 | Security architecture | F, KA | 3 | 0.1 | Ayan - 100%
11 | As a business, I want to know when popular events are happening nearby so that I can prepare for increased pedestrian traffic. | 1. Decide on a metric for popular events (e.g. certain number of committed attendees). 2. Learn how to implement a subscription or notification system to inform users of popular events. 3. Implement the event subscription/notification system. | 6 | Environment creation | F, KA | 4 | 1 | Sean - 100%
13 | As a user, I want to be able to use hashtags on my events so that I can easily filter out events I am not interested in. | 1. Learn how to add tags as part of event details objects. 2. Learn how to sort and filter events based on selected tags. 3. Implement tag filtering on the map. 4. Implement tag sorting and filtering on the event list. | 6 | Environment creation | F, KA | 2 | 1 | Nicole - 100%
14 | As a user, I want to be able to choose who can see my event details so that I can prevent unwanted people from attending. | 1. Learn how to implement access and visibility rules for events. 2. Implement settings that allow users to choose the visibility of their events. | 6 | Environment creation | F, KA | 3
15 | As an event-planner, I want to be able to generate a link for my event so that I can send it to others. | 1. Learn how to support and generate URLs for event objects. 2. Implement a button that allows users to get a URL for a selected event. | 6 | Environment creation | F, KA | 1
16 | As a regular user, I want to be able to set up a recurring event, so that I can avoid the hassle of reposting the same event repeatedly. | 1. Learn how to implement events. 2. Implement recurring events. | 6 | Environment creation | F, KA | 2
17 | As a regular user, I want to be able to see a history of events I have planned and attended so that I can view what I have done previously. | 1. Create the history events page. 2. Learn how to log and display events that have been attended. | 6 | Environment creation | F, KA | 4
18 | As a commuter, I want to be able to see where the closest parking spots are for a certain event so that I can reduce walking time to the event. | 1. Learn how to use Google Maps to locate parking spots. 2. Learn how to calculate the distance between sets of points in Google Maps. 3. Implement a popup that shows the distance between a selected event and the nearest parking spot. | 6 | Environment creation | F, KA | 3

## Sprint Backlog 5
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
8 | As a fraternity member, I want to be able to advertise my events so that I can increase participation. | 1. Learn how to create events | 5 | Environment creation | F, KA | 3
9 | As a user, I want my data to be secure so that sensitive information is not exposed. | 1. Learn gather user data 2. Learn how to implement proper security architecture surrounding user data | 5 | Security Architecture | F, KA | 3
10 | As a user, I want multifactor authentication so that my account is secure. | 1. Learn how to implement MFA login 2. Create an option to turn MFA on in profile | 5 | Security Architecture | F, KA | 3
11 | As a business, I want to know when popular events are happening nearby so that I can prepare for increased pedestrian traffic. | 1. Learn how to create events 2. Gather numbers of users going to event and display the number | 5 | Environment creation | F, KA | 4
15 | As an event-planner, I want to be able to generate a link for my event so that I can send it to others. | 1. Learn how to create events 2. Find an API to generate links for a url | 5 | Environment creation | F, KA | 1
17 | As a regular user, I want to be able to see a history of events I have planned and attended so that I can view what I have done previously. | 1. Learn how to create events 2. Create the history on user profile | 5 | Environment creation | F, KA | 4
22 | As a user, I want to recieve daily updates so that I don't miss out on any events. | 1. Learn how to create a subscription list 2. Learn how to send a newsletter to users 3. Implement the newsletter and subscription form | 5 | Environment creation | F, KA | 2 | 2 | Sean - 100%
23 | As a user, I want to be able to contact the developers so that I can report issues. | 1. Research the best avenues for contacting developers (email, GitHub, ...) 2. Implement a contact form | 5 | Environment creation | F, KA | 2 | 2 | Sean - 100%
24 | As a user, I want to view the privacy policy so that I know how my data is being used. | 1. Research how to write a privacy policy 2. Create the privacy policy page | 5 | Environment creation | F, KA | 2 | 2 | Sean - 100%
25 | As a user, I want to view the terms and conditions so that I know the legal agreements I make with UMaine Connect when I use their platform. | 1. Research how to write terms and conditions 2. Create the terms and conditions page | 5 | Environment creation | F, KA | 2 | 2 | Sean - 100%

## Sprint Backlog 4
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
1 | As a student, I want to know where study sessions are being held so that I can prepare for exams with my classmates. | 1. Learn how to put events on the map 2. Create event list | 4 | Environment creation | F, KA | 4 | 1 | Nicole - 100%
2 | As an event organizer, I want to know the number of people planning to come to my events so that I can properly prepare concessions and seating. | 1. Learn how to create events 2. Gather numbers of users going to event and display the number | 4 | Environment creation | F, KA | 4 | 0
5 | As a member of the University of Maine Police department, I want to know where the big events are so that I can keep people safe. | 1. The larger number of people going to an event, the larger the event icon should be | 4 | Environment creation | F, KA | 3 | 0
6 | As a user, I want to be able to sort events by most to least popular so that I can go to an event with a gathering size I’m comfortable with. | 1. Create event list 2. Create filter for event list | 4 | Environment creation | F, KA | 2 | 0
7 | As a campus faculty member, I want to know what students are doing around campus, so that we can best support their interests. | 1. Learn how to put events on the map 2. Create event list | 4 | Environment creation | F, KA | 3 | 0
21 | As a student, I want to create an event for meeting at the union so that I can get lunch with friends. | 1. Learn how to create events | 4 | Environment creation | F, KA | 3 | 0

## Sprint Backlog 3
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
20 | As a user, I want to customize my profile so that others can learn more about me prior to events. | 1. Learn how to accept input from users and store it in the database 2. Create profile page 3. Implement profile customization fields and options | 3 | Environment Creation | F, KA | 3 | 1 | Andres - 100%

## Sprint Backlog 2
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
12 | As a user, I want to be able to log in to my account so I can see events I have committed to. | 1. Learn how to connect with Firebase 2. Implement authentication 3. Representing user data 4. create a login page. | 2 | Environment creation | F, KA | 3 | 3 | Noah - 100%
19 | As a user, I want to create a profile so that I can identify myself when I sign up for events. | 1. Learn how to connect with Firebase 2. implement authentication 3. representing user data 4. create a user page. | 2 | Environment creation | F, KA | 4 | 4 | Noah - 75% Andres - 25%

## Sprint Backlog 1
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
1 | As a student, I want to know where study sessions are being held so that I can prepare for exams with my classmates. | 1. Create the main landing page 2. Implement Google Maps 3. Create location and description on maps for events | 1 | Environment creation | F, KA | 4 | 2 | Sean - 100%
5 | As a member of the University of Maine Police department, I want to know where the big events are so that I can keep people safe. | 1. Create the main landing page 2. Implement Google maps 3. Create location and description on map for events | 1 | Environment creation | F, KA | 3 | 1 | Sean - 100%
18 | As a commuter, I want to be able to see where the closest parking spots are for a certain event so that I can reduce walking time to the event. | 1. Create the main landing page 2. Implement Google maps 3. Create location and description on map for events | 1 | Environment Creation | F, KA | 3 | 1 | Sean - 100%
21 | As a student, I want to create an event for meeting at the union so that I can get lunch with friends. | 1. Create the main landing page 2. Implement Goolge maps 3. Create event creation system | 1 | Environment Creation | F, KA | 3 | 1 | Sean - 100%