## Sheet1
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
12 | As a user, I want to be able to log in to my account so I can see events I have committed to. | 1. Learn how to connect with Firebase 2. Implement authentication 3. Representing user data 4. create a login page. | 2 | Environment creation | F, KA | 3 | 2 | Noah - 100%
19 | As a user, I want to create a profile so that I can identify myself when I sign up for events. | 1. Learn how to connect with Firebase 2. implement authentication 3. representing user data 4. create a user page. | 2 | Environment creation | F, KA | 4 | 3 | Noah - 100%
1 | As a student, I want to know where study sessions are being held so that I can prepare for exams with my classmates. | 1. Create the main landing page 2. Implement Google Maps 3. Create location and description on maps for events | 1 | Environment creation | F, KA | 4 | 2 | Sean - 100%
5 | As a member of the University of Maine Police department, I want to know where the big events are so that I can keep people safe. | 1. Create the main landing page 2. Implement Google maps 3. Create location and description on map for events | 1 | Environment creation | F, KA | 3 | 1 | Sean - 100%
18 | As a commuter, I want to be able to see where the closest parking spots are for a certain event so that I can reduce walking time to the event. | 1. Create the main landing page 2. Implement Google maps 3. Create location and description on map for events | 1 | Environment Creation | F, KA | 3 | 1 | Sean - 100%
21 | As a student, I want to create an event for meeting at the union so that I can get lunch with friends. | 1. Create the main landing page 2. Implement Goolge maps 3. Create event creation system | 1 | Environment Creation | F, KA | 3 | 1 | Sean - 100%