## Sprint Backlog 4
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
1 | As a student, I want to know where study sessions are being held so that I can prepare for exams with my classmates. | 1. Learn how to put events on the map 2. Create event list | 4 | Environment creation | F, KA | 4 | 1 | Nicole - 100%
2 | As an event organizer, I want to know the number of people planning to come to my events so that I can properly prepare concessions and seating. | 1. Learn how to create events 2. Gather numbers of users going to event and display the number | 4 | Environment creation | F, KA | 4 | 0
5 | As a member of the University of Maine Police department, I want to know where the big events are so that I can keep people safe. | 1. The larger number of people going to an event, the larger the event icon should be | 4 | Environment creation | F, KA | 3 | 0
6 | As a user, I want to be able to sort events by most to least popular so that I can go to an event with a gathering size I’m comfortable with. | 1. Create event list 2. Create filter for event list | 4 | Environment creation | F, KA | 2 | 0
7 | As a campus faculty member, I want to know what students are doing around campus, so that we can best support their interests. | 1. Learn how to put events on the map 2. Create event list | 4 | Environment creation | F, KA | 3 | 0
21 | As a student, I want to create an event for meeting at the union so that I can get lunch with friends. | 1. Learn how to create events | 4 | Environment creation | F, KA | 3 | 0

## Sprint Backlog 3
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
20 | As a user, I want to customize my profile so that others can learn more about me prior to events. | 1. Learn how to accept input from users and store it in the database 2. Create profile page 3. Implement profile customization fields and options | 3 | Environment Creation | F, KA | 3 | 1 | Andres - 100%

## Sprint Backlog 2
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
12 | As a user, I want to be able to log in to my account so I can see events I have committed to. | 1. Learn how to connect with Firebase 2. Implement authentication 3. Representing user data 4. create a login page. | 2 | Environment creation | F, KA | 3 | 3 | Noah - 100%
19 | As a user, I want to create a profile so that I can identify myself when I sign up for events. | 1. Learn how to connect with Firebase 2. implement authentication 3. representing user data 4. create a user page. | 2 | Environment creation | F, KA | 4 | 4 | Noah - 75% Andres - 25%

## Sprint Backlog 1
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
1 | As a student, I want to know where study sessions are being held so that I can prepare for exams with my classmates. | 1. Create the main landing page 2. Implement Google Maps 3. Create location and description on maps for events | 1 | Environment creation | F, KA | 4 | 2 | Sean - 100%
5 | As a member of the University of Maine Police department, I want to know where the big events are so that I can keep people safe. | 1. Create the main landing page 2. Implement Google maps 3. Create location and description on map for events | 1 | Environment creation | F, KA | 3 | 1 | Sean - 100%
18 | As a commuter, I want to be able to see where the closest parking spots are for a certain event so that I can reduce walking time to the event. | 1. Create the main landing page 2. Implement Google maps 3. Create location and description on map for events | 1 | Environment Creation | F, KA | 3 | 1 | Sean - 100%
21 | As a student, I want to create an event for meeting at the union so that I can get lunch with friends. | 1. Create the main landing page 2. Implement Goolge maps 3. Create event creation system | 1 | Environment Creation | F, KA | 3 | 1 | Sean - 100%